## Daily Progress Report
Date | Activity ID | Activity Description | Discipline | % Complete | Actual Start | Actual Finish | Location | Remarks
2026-08-29 | PIP-002 | Erect Line 24-XX spool at chainage 12+450 | Piping | 60 | 2026-08-27 09:30 |  | Chainage 12+450 | 6 joints completed out of 10
2026-08-29 | PIP-003 | Hydrotest Line 24-XX section N12 to N15 | Piping | 0 |  |  | N12-N15 | Scheduled for 2026-09-02
2026-08-29 | CIV-002 | Concrete pour for Pump P-101 foundation | Civil | 100 | 2026-08-28 07:00 | 2026-08-28 16:00 | Area A Grid 12-13 | Completed as per plan
2026-08-29 | ELE-001 | Cable pulling MCC-1 to P-101 Route R-12 | Electrical | 40 | 2026-08-27 08:00 |  | Route R-12 | 240m of 360m complete
2026-08-29 | MEC-001 | Set pump P-101 on foundation | Mechanical | 100 | 2026-08-29 09:00 | 2026-08-29 14:00 | Area A | Leveled and grouted